Smart Parking Platform Project Management Plan

Homework 1

1. Existing Software Landscape Research

ParkMobile

Overview

ParkMobile is a mobile parking application that lets users locate, reserve, and pay for parking spaces through a smartphone app.

Strengths

- Easy mobile payments

- Large user base

- Supports reservations

Weaknesses

- Limited real-time occupancy information

- Availability varies by city

SpotHero

Overview

SpotHero enables drivers to find and reserve parking spaces before arriving at a destination.

Strengths

- Strong reservation functionality

- Extensive parking network

Weaknesses

- Focused mainly on major cities

- Limited occupancy analytics

BestParking

Overview

BestParking helps users compare parking rates and locate nearby parking facilities.

Strengths

- Price comparison tools

- Wide geographic coverage

Weaknesses

- Limited management features for operators

- Few reporting capabilities

How Our Application Will Be Different

The Smart Parking Platform will include:

- Real-time occupancy tracking

- Interactive availability maps

- Parking occupancy forecasting

- Dynamic pricing recommendations

- Enhanced operator dashboards

- Advanced analytics and reporting

- Reservation reminders and notifications

- Navigation integration

2. Vision and Scope

Project Acquisition

WE ARE $oftware Corp. was contracted by a consortium of parking facility operators and city transportation stakeholders seeking a modern parking management solution. The goal is to reduce time spent searching for parking while improving parking facility management.

Company Background

WE ARE $oftware Corp. is a fictional software development company specializing in web and mobile applications. For this academic project, the company has unlimited development resources and budget.

Vision Statement

The vision of the Smart Parking Platform is to create convenient, efficient, and intelligent parking experience for drivers while providing operators with powerful management and reporting tools.

Project Overview

The Smart Parking Platform will provide:

- Mobile application

- Web application

- Real-time parking availability

- Parking reservations

- Digital payment processing

- Notifications and alerts

- Administrative dashboards

- Analytics and reporting

Scope

In Scope

- User registration

- Authentication

- Parking search

- Real-time parking availability

- Reservations

- Payments

- Receipts

- Notifications

- Operator dashboards

- Reports and analytics

Out of Scope

- Parking hardware installation

- Vehicle maintenance services

- Traffic law enforcement

- Autonomous vehicle parking

3. Software Requirements Specification (SRS) Draft

Purpose

The purpose of this system is to help drivers locate, reserve, navigate to, and pay for parking spaces while allowing parking operators to manage occupancy and revenue.

Actors

- Driver

- Parking Operator

- System Administrator

- Finance Personnel

- Payment Provider

Use Cases

UC-01 User Registration

Actor: Driver
Description: Create a new account.

UC-02 User Login

Actor: Driver
Description: Log in to the system.

UC-03 Password Reset

Actor: Driver
Description: Reset a forgotten password.

UC-04 Search for Parking Locations

Actor: Driver
Description: Search for nearby parking.

UC-05 View Availability

Actor: Driver
Description: View of available parking spaces.

UC-06 Reserve Parking Space

Actor: Driver
Description: Reserve a parking space.

UC-07 Modify Reservation

Actor: Driver
Description: Change reservation details.

UC-08 Cancel Reservation

Actor: Driver
Description: Cancel reservation.

UC-09 Navigate to Location

Actor: Driver
Description: Receive directions to a parking facility.

UC-10 Process Payment

Actor: Driver
Description: Pay for parking electronically.

UC-11 Receive Receipt

Actor: Driver
Description: Receive a digital receipt after payment.

UC-12 Receive Notifications

Actor: Driver
Description: Receive reminders and alerts.

UC-13 Manage Parking Inventory

Actor: Parking Operator
Description: Add and update parking spaces.

UC-14 Monitor Occupancy

Actor: Parking Operator
Description: View occupancy in real time.

UC-15 Generate Reports

Actor: Parking Operator
Description: Create utilization and revenue reports.

UC-16 Dynamic Pricing

Actor: Parking Operator
Description: Adjust pricing based on demand.

UC-17 Manage User Accounts

Actor: System Administrator
Description: Manage system users.

UC-18 Payment Reconciliation

Actor: Finance Personnel
Description: Verify payment transactions.

UC-19 Predict Availability

Actor: Driver
Description: View expected future parking availability.

UC-20 Audit Logs

Actor: System Administrator
Description: Review system activity logs.

# Homework 2 Section

# 4. Work Breakdown Structure (WBS)

## 1.0 Smart Parking Platform Project

### 1.1 Project Management

#### 1.1.1 Project Charter

- Define project objectives

- Define stakeholders

- Obtain approval

#### 1.1.2 Planning

- Create schedule

- Develop risk plan

- Develop communication plan

#### 1.1.3 Monitoring & Control

- Weekly status reviews

- Progress tracking

- Change management

### 1.2 Requirements & Design

#### 1.2.1 Requirements Gathering

- Stakeholder interviews

- Surveys

- Requirement documentation

#### 1.2.2 System Design

- Architecture design

- Database design

- API design

#### 1.2.3 UI/UX Design

- Mobile wireframes

- Web wireframes

- Dashboard mockups

### 1.3 Authentication Module

#### 1.3.1 User Registration

- Create account

- Email verification

- Password validation

#### 1.3.2 Login

- Username/password login

- MFA support

- Session management

#### 1.3.3 Account Recovery

- Password reset

- Account unlock

### 1.4 Parking Management Module

#### 1.4.1 Parking Search

- Search nearby garages

- Filter results

- View parking details

#### 1.4.2 Availability Tracking

- Real-time updates

- Occupancy monitoring

- Availability forecasting

#### 1.4.3 Reservation System

- Create reservation

- Modify reservation

- Cancel reservation

### 1.5 Payment Module

#### 1.5.1 Payment Processing

- Credit card payments

- Digital wallet payments

- Transaction verification

#### 1.5.2 Billing

- Receipt generation

- Refund processing

- Payment history

#### 1.5.3 Financial Reporting

- Revenue summaries

- Transaction reports

### 1.6 Operator Dashboard

#### 1.6.1 Garage Management

- Add garage

- Edit garage

- Remove garage

#### 1.6.2 Occupancy Monitoring

- Real-time occupancy

- Capacity management

#### 1.6.3 Pricing Management

- Set pricing

- Dynamic pricing

### 1.7 Reporting & Analytics

#### 1.7.1 Occupancy Reports

- Daily reports

- Weekly reports

- Monthly reports

#### 1.7.2 Revenue Reports

- Revenue summaries

- Financial exports

#### 1.7.3 Analytics Dashboard

- Utilization metrics

- Forecasting

### 1.8 Testing & Deployment

#### 1.8.1 Testing

- Unit testing

- Integration testing

- Security testing

#### 1.8.2 User Acceptance Testing

- Stakeholder review

- Issue tracking

#### 1.8.3 Deployment

- Production deployment

- Monitoring

- Support

# 5. Project Timeline

| Week | Activity |
| --- | --- |
| 1 | Project Charter & Stakeholders |
| 2 | Research & Competitive Analysis |
| 3 | Requirements Gathering |
| 4 | Vision and Scope Finalization |
| 5 | WBS Development |
| 6 | Schedule & Gantt Chart |
| 7 | System Architecture |
| 8 | UI/UX Design |
| 9 | Backend/API Planning |
| 10 | Payment Integration Planning |
| 11 | Security Planning |
| 12 | Quality Assurance Planning |
| 13 | Risk Management |
| 14 | Communication Plan |
| 15 | Final Project Review |
| 16 | Final Submission |

# Milestones

## Project Milestones

### Milestone 1

Project Initiation Complete

- Week 2

### Milestone 2

Requirements Approved

- Week 5

### Milestone 3

Architecture Complete

- Week 8

### Milestone 4

Testing Plan Complete

- Week 12

### Milestone 5

Final Project Document Complete

- Week 16

### Gantt Chart

| Task | W1 | W2 | W3 | W4 | W5 | W6 |
| --- | --- | --- | --- | --- | --- | --- |
| Competitive Analysis Research | X | X |  |  |  |  |
| Vision & Scope Development |  | X | X |  |  |  |
| SRS & Use Cases |  | X | X |  |  |  |
| Work Breakdown Structure (WBS) |  |  | X |  |  |  |
| Project Timeline Development |  |  | X | X |  |  |
| System Design & Architecture |  |  |  | X | X |  |
| UI/UX Planning |  |  |  | X | X |  |
| Payment Integration Planning |  |  |  |  | X |  |
| Security Planning |  |  |  |  | X |  |
| Testing Strategy |  |  |  |  |  | X |
| Final Documentation Updates |  |  |  |  |  | X |

Homework 3

8.1 Product Backlog

The Product Backlog contains all features identified for the Smart Parking Platform. Features were organized into Login, User Interface, Backend Services, and Reporting categories.

Login

- User Registration

- User Login

- Password Reset

- Multi-Factor Authentication

- Session Management

UI

- Driver Dashboard

- Operator Dashboard

- User Profile

- Edit Profile

- Parking Search

- Map View

- Garage Details

- Reservation Screen

- Reservation History

- Payment Screen

- Receipt Screen

- Notifications

- Garage Management

- Occupancy Dashboard

- Pricing Management

Backend

- User Authentication Service

- Account Management

- Parking Availability Service

- Reservation Processing

- Reservation Cancellation

- Inventory Management

- Payment Gateway Integration

- Payment Validation

- Receipt Generation

- Notification Service

- Occupancy Monitoring

- Analytics Collection

- Report Generation

- Role-Based Access Control

- Audit Logging

Reporting

- Daily Occupancy Report

- Weekly Occupancy Report

- Monthly Occupancy Report

- Revenue Report

- Reservation Report

- Cancellation Report

- Peak Usage Report

- Utilization Report

- User Activity Report

- Financial Export Report

8.2 Sprint 1 Backlog

Sprint 1 focuses on core user functionality required for initial platform operation.

- User Registration

- User Login

- Password Reset

- Driver Dashboard

- Parking Search

- Map View

- User Authentication Service

- Account Management

- Parking Availability Service

- Reservation Processing

- Notification Service

8.3 Trello Board

Figure 2. Smart Parking Platform Product Backlog and Sprint 1 Backlog

Homework 4

## 9. Risk Management Plan

### 9.1 Risk Categories

### Technical Risks

- Third-party API failure (mapping or payment services)

- Real-time parking data inaccuracies

- Security vulnerabilities and data breaches

- System performance issues under high user load

### Schedule Risks

- Delays in requirements gathering

- Integration testing takes longer than planned

- Stakeholder feedback delays

- Scope creep increases project duration

### Financial Risks

- Unexpected cloud infrastructure costs

- Third-party service fee increases

- Additional security compliance costs

- Cost overruns from additional project requirements

### People Risks

- Key team member unavailable

- Communication breakdown between teams

- Lack of stakeholder engagement

- Insufficient testing resources

# 9.2 Risk Register

Use this directly in Word:

| ID | Risk Description | Probability | Impact | Owner | Response Strategy | Status |
| --- | --- | --- | --- | --- | --- | --- |
| R1 | Payment API Failure | Medium | High | Payment Team | Backup payment provider | Open |
| R2 | Mapping Service Outage | Medium | High | Mapping Team | Secondary map provider | Open |
| R3 | Real-Time Data Delay | High | Medium | Backend Team | Monitoring and optimization | Open |
| R4 | Security Breach | Low | Very High | Security Team | Security audits and encryption | Open |
| R5 | Scope Creep | High | High | Project Manager | Change control process | Open |
| R6 | Delayed Testing | Medium | High | QA Team | Early testing schedule | Open |
| R7 | Stakeholder Feedback Delays | Medium | Medium | Project Manager | Scheduled reviews | Open |
| R8 | Key Team Member Loss | Low | High | Project Manager | Cross-training | Open |
| R9 | Cloud Service Downtime | Low | High | Infrastructure Team | Redundant hosting | Open |
| R10 | Cost Estimate Changes | Medium | Medium | Finance Team | Budget reserve planning | Open |

# 10. Communication Plan

## Purpose

The Communication Plan defines how project stakeholders and team members will communicate throughout the Smart Parking Platform project.

## Team Meeting Cadence

| Team | Meeting Type | Frequency |
| --- | --- | --- |
| Project Management | Status Meeting | Weekly |
| Mobile Development Team | Scrum Meeting | Daily |
| Web Development Team | Scrum Meeting | Daily |
| Backend/API Team | Scrum Meeting | Daily |
| Mapping Team | Technical Review | Weekly |
| Payment Team | Integration Review | Weekly |
| QA Team | Testing Review | Weekly |
| Stakeholders | Progress Review | Bi-Weekly |

## Reporting Methods

### Weekly Status Reports

Used to communicate:

- Progress

- Risks

- Issues

- Upcoming work

### Stakeholder Presentations

Provided every two weeks and include:

- Project status

- Milestone progress

- Risk updates

### Project Repository

GitHub serves as the primary documentation repository.

### Video Updates

Weekly stakeholder videos summarize completed work and upcoming activities.

Homework 5

# 11. Roles & Resources Plan

## Team Resources

| Resource Name | Role | Skill Level | Allocation % |
| --- | --- | --- | --- |
| Sarah Johnson | Project Manager | Senior | 100% |
| Michael Chen | Business Analyst | Senior | 75% |
| Jessica Williams | Mobile Developer | Senior | 100% |
| David Garcia | Web Developer | Mid-Level | 100% |
| Emily Rodriguez | Backend/API Developer | Senior | 100% |
| James Mitchell | Database Engineer | Mid-Level | 75% |
| Sophia Brown | Mapping Services Developer | Mid-Level | 50% |
| Daniel Lee | Payment Integration Specialist | Senior | 50% |
| Olivia Martin | QA/Test Engineer | Senior | 100% |
| Ethan Thompson | System Administrator | Mid-Level | 50% |

### Assumptions

- Senior resources have 5+ years of experience.

- Mid-Level resources have 2-5 years of experience.

- Unlimited budget is available, but realistic estimates are documented.

- Resources may support multiple project activities.

# 12. Resource & Cost Plan

## Cost Estimation Method

Bottom-Up Estimating

Project costs were estimated by identifying resources, estimating monthly labor costs, and rolling them up to produce the total project budget.

## Estimated Monthly Resource Costs

| Role | Monthly Cost |
| --- | --- |
| Project Manager | $12,000 |
| Business Analyst | $9,000 |
| Mobile Developer | $10,000 |
| Web Developer | $8,000 |
| Backend Developer | $10,000 |
| Database Engineer | $8,500 |
| Mapping Specialist | $7,500 |
| Payment Specialist | $8,000 |
| QA Engineer | $8,000 |
| System Administrator | $7,500 |

### Total Monthly Cost

Plain Text

$88,500 per month

## Project Cash Flow

| Month | Planned Spending |
| --- | --- |
| Month 1 | $88,500 |
| Month 2 | $88,500 |
| Month 3 | $88,500 |
| Month 4 | $88,500 |

### Estimated Semester Cost

Plain Text

$354,000

Calculation:

Plain Text

$88,500 × 4 Months = $354,000

# 13. RACI Matrix

### Key

- R = Responsible

- A = Accountable

- C = Consulted

- I = Informed

| Activity | PM | BA | Mobile | Web | Backend | QA | Stakeholders |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Requirements Gathering | A | R | I | I | I | I | C |
| Scope Definition | A | R | I | I | I | I | C |
| UI Design | A | C | R | R | I | I | I |
| Authentication Module | A | C | R | R | R | C | I |
| Parking Search Feature | A | C | R | R | R | C | I |
| Reservation System | A | C | R | R | R | C | I |
| Payment Integration | A | C | I | I | R | C | I |
| Reporting & Analytics | A | C | I | R | R | C | I |
| Testing | I | I | C | C | C | A/R | I |
| Deployment | A | I | I | I | R | C | I |
| Project Approval | C | I | I | I | I | I | A |

# Homework 6

# 1. Update SRS

Before:

Plain Text

UC-01 User Registration

Actor: Driver

Description: Create a new account.

After:

Plain Text

UC-01 User Registration

Actor: Driver

Goal:

Create a new user account.

Preconditions:

User is not registered.

Main Flow:

1. User selects Register.

2. User enters account information.

3. System validates information.

4. System creates account.

5. User receives confirmation.

Postconditions:

Account is successfully created.

Try expanding at least 5-10 of your most important use cases.

# 2. Update User Stories

Plain Text

US-01

As a driver,

I want to search nearby parking garages,

so that I can find available parking quickly.

US-02

As a driver,

I want to reserve a parking space,

so that I can guarantee parking before arriving.

US-03

As a driver,

I want to pay online,

so that I don't have to use a parking kiosk.

US-04

As a parking operator,

I want to monitor occupancy,

so that I can improve garage utilization.

US-05

As a parking operator,

I want to generate reports,

so that I can analyze usage trends.

Add 8-10 of these.

# 3. Update WBS

Before:

Plain Text

1.3 Payment Module

1.3.1 Process Payment

After:

Plain Text

1.3 Payment Module

1.3.1 Credit Card Processing

1.3.2 Mobile Wallet Processing

1.3.3 Receipt Generation

1.3.4 Refund Processing

Your professor specifically wants things as complete as possible.

# 4. Update Timeline & Gantt Chart

Plain Text

W1-W2 Research

W3-W4 Requirements

W5 WBS

W6 Cost Planning

W7 Risk Management

W8 Communication Planning

W9 Design

W10 Architecture

W11 Security

W12 Testing

W13 Documentation

W14 Review

W15 Final Updates

W16 Submission

Update the Gantt chart to reflect the expanded schedule.

# 5. Update Backlog

### Login

Plain Text

Session Timeout

Remember Me

Email Verification

### Backend

Plain Text

Fraud Detection

Rate Limiting

System Monitoring

### Reporting

Plain Text

Parking Demand Forecast

Payment Trends Report

# 6. Update Sprint Planning

Added Sprint 2.

## Sprint 1

Core user functionality.

## Sprint 2

Plain Text

Reservation History

Operator Dashboard

Payment Processing

Receipt Generation

Notifications

Take a new Trello/Jira screenshot.

Replace the old screenshot in the document.

# 7. Update Risks

Plain Text

R11 Data Privacy Compliance

R12 Fraudulent Transactions

R13 Excessive API Costs

R14 Poor User Adoption

R15 Inaccurate Parking Sensor Data

# 8. Update Communication Plan

Plain Text

Executive Stakeholder Meeting

Monthly

Sprint Review

Bi-Weekly

Sprint Retrospective

Bi-Weekly

Daily Standups

Daily

# 9. Update Roles

Add stakeholders

Plain Text

Finance Analyst

City Transportation Liaison

Security Specialist

# 10. Update Cost Plan

Plain Text

Cloud Hosting

Mapping APIs

Payment Gateway Fees

Security Audits

Contingency Reserve

# 11. Update RACI Matrix

Plain Text

Risk Management

Security Planning

Compliance Reviews

Stakeholder Presentations

Sprint Planning

# Homework 7

# 14. Stakeholder Analysis

Add this section to your Project-Management-Plan.docx.

## Power-Interest Grid

### High Power / High Interest (Manage Closely)

- Parking Facility Operators

- City Transportation Departments

- Project Sponsor

- System Administrators

### High Power / Low Interest (Keep Satisfied)

- Finance and Billing Personnel

- Third-Party Payment Providers

### Low Power / High Interest (Keep Informed)

- Drivers and Vehicle Owners

- Mobile Application Users

### Low Power / Low Interest (Monitor)

- General Public

- Non-Participating Parking Facilities

## Stakeholder Analysis Table

| Stakeholder | Power | Interest | Management Strategy |
| --- | --- | --- | --- |
| Parking Operators | High | High | Manage Closely |
| City Transportation Departments | High | High | Manage Closely |
| System Administrators | High | High | Manage Closely |
| Finance Personnel | High | Low | Keep Satisfied |
| Payment Providers | High | Low | Keep Satisfied |
| Drivers | Low | High | Keep Informed |
| Mobile App Users | Low | High | Keep Informed |
| General Public | Low | Low | Monitor |

# Power-Interest Grid Diagram

You can paste this into Word or recreate it with shapes.

Plain Text

HIGH INTEREST

↑

KEEP INFORMED | MANAGE CLOSELY

|

Drivers | Parking Operators

Mobile Users | City Transportation

| System Administrators

------------------------------------------------------------→ HIGH POWER

|

MONITOR | KEEP SATISFIED

|

General Public | Finance Personnel

| Payment Providers

↓

LOW INTEREST

Caption:

Plain Text

Figure 4. Smart Parking Platform Power-Interest Grid

# 15. Team Charter

## Team Charter

### Team Name

WE ARE $oftware Corp.

### Mission Statement

Develop a Smart Parking Platform that enables drivers to locate, reserve, navigate to, and pay for parking spaces while providing operators with powerful management and reporting capabilities.

### Team Members

- Sarah Johnson – Project Manager

- Michael Chen – Business Analyst

- Jessica Williams – Mobile Developer

- David Garcia – Web Developer

- Emily Rodriguez – Backend Developer

- Olivia Martin – QA Engineer

### Team Values

- Accountability

- Collaboration

- Respect

- Innovation

- Communication

### Team Expectations

- Attend scheduled meetings

- Meet deadlines

- Communicate issues early

- Support team members

- Maintain quality standards

### Conflict Resolution

Conflicts will be discussed during team meetings. Unresolved conflicts will be escalated to the Project Manager.

### Decision Making

Major project decisions will be made by consensus with final approval from the Project Manager.

# 16. Project Charter

## Project Charter

### Project Name

Smart Parking Platform

### Project Sponsor

Consortium of Parking Operators and City Transportation Departments

### Project Manager

Sarah Johnson

### Business Need

Drivers spend significant time searching for parking, resulting in congestion, wasted fuel, and lost productivity. Parking operators require improved tools to manage occupancy and maximize parking utilization.

### Project Objective

Develop a web and mobile platform that allows users to:

- Locate parking spaces

- View real-time availability

- Reserve parking

- Pay electronically

- Receive notifications

And allows operators to:

- Manage garages

- Monitor occupancy

- Generate reports

- Analyze parking utilization

### Project Scope

#### Included

- User registration

- Authentication

- Parking search

- Reservations

- Payment processing

- Reporting dashboards

- Notifications

#### Excluded

- Physical parking sensors

- Vehicle maintenance

- Traffic law enforcement

### Success Criteria

- Real-time parking visibility

- Secure payment processing

- High user satisfaction

- Increased parking utilization

- Successful semester project completion

### Major Constraints

- Fixed semester timeline

- Third-party API dependencies

- Security and privacy compliance requirements

### Major Risks

- API failures

- Schedule delays

- Security concerns

- Stakeholder communication issues